## Requirement Document
Time card requirments
# | Task | Category | Owner | Status | Stage | Estimated Delivery | Complexity | Priority
1 | Single project ID for entire month (i.e. 5 weeks) in short hard coded weeks, excluding sat-sun | Happy Path | Ankit, Keerthi & Arfin | Covered | Complete | 2017-12-25 | Simple | Low
2 | Single project ID for entire month (i.e. 4-5-6 weeks) in short depends upon months week, excluding sat-sun | Happy Path | Ankit, Keerthi & Arfin | Covered | Complete | 2017-12-25 | Simple | Low
3 | Single project ID for entire month in short not hard coded weeks, including start and end dates | Happy Path | Ankit, Keerthi & Arfin | Covered | Complete | 2017-12-25 | Simple | Low
4 | Shift-Roster | Happy Path | Ankit, Keerthi & Arfin | Covered | Complete | 2017-12-25 | Simple | Medium
5 | Multiple project ID for entire month in short not hard coded weeks, including start and end dates | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Complex | High
6 | Planned leaves -- Only One Leave Code | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Medium | High
7 | Public holidays by location need to check dates and fill the timecard | Stage 2 | Keerthi | Covered | Complete | 2018-01-10 | Complex | High
8 | Resignation, project release case -- For Specific date range we need to fill timecard | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Medium | High
9 | Training code case based on user | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Medium | High
10 | Exception Handling With Proper Error Messages / Maintain Log Files | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Complex | High
11 | Notification to Manager or Approver | Stage 2 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Simple | High
12 | Work on Multiple Excels For Various Accounts | Stage 3 | Praveen & Vamsi | Covered | Complete | 2018-01-10 | Simple | Medium
13 | Planned leaves -- Multiple Types Of Leave At Once | Stage 3 | Praveen | WIP | Testing | 2018-01-25 | Simple | High
14 | Auto Approval PM | Stage 3 | Ankit To Discuss With Raji | Not Started | TBD | TBD | TBD | TBD
15 | Overwrite Timecard In Case Of Saved Ones | Stage 3 | Praveen | WIP | Testing | 2018-01-25 | Medium | Low
16 | Create a DL/Troom Link to Automate The Communication | Stage 3 | Rahul | WIP | Development | 2018-01-25 | Simple | Low
17 | Weekend working or Public Holiday working - On Call | Stage 3 | Keerthi | WIP | Development | 2018-01-25 | Medium | High
18 | Coloring The Failed Rows | Stage 3 | Vamsi | WIP | Testing | 2018-01-25 | Medium | Medium
19 | Add BT, NBT hours in mail body --- Reporting | Stage 3 | Vamsi | WIP | Testing | 2018-01-25 | Medium | Medium
20 | Report Generation For DM - Database Fetch & Update | Stage 3 | Vamsi | WIP | Development | 2018-01-25 | Complex | High
20 | Onsite Time Card Filling - Replicon | Stage 4 | TBD | TBD | TBD | TBD | TBD | TBD

## Excel Format
Sr. No | Name | User ID | Project Codes(separated by ;) | From Date | To Date | BT(separated by ;) | NBT(separated by ;) | Shift | Region | Leave Code | Leave Dates | Leave Type | Training Code | Training Dates | Weekend Project Code | Weekend Dates | Weekend Billable Hours | EM Email | Final Status | Total BT Hours For Month | Total NBT Hours For Month | Total Leave Hours For Month | Week 1 Status | Week 1 Comments | Week 2 Status | Week 2 Comments | Week 3 Status | Week 3 Comments | Week 4 Status | Week 4 Comments | Week 5 Status | Week 5 Comments
1 | nikhil shinde | nshinde1 | 100442082;100442084 | 2;1 | 31;31 | 4;4 | 0;1 | General Shift - HC | Mumbai | - | - |  | - | -
Dynamically Generated
Already Present In the Input

## Test Scenarios
Single Project IDs
# | Test Scenarios | Test Data (To be prepared)
1 | Single project ID for entire month - starting from beginning of month to end of month - No Leaves/ No Training | WIP
2 | Single project ID for entire month - starting from beginning/middle of month to middle/end of month - No Leaves/ No Training | WIP
3 | Single Project ID for entire month with Leave - no training code | WIP
4 | Single Project ID for entire month with training code - no leave | WIP
5 | Single Project ID for entire month with leaves and single/multiple training code | WIP
Multiple Project IDs
6 | Multiple project IDs for entire month - starting from beginning of month to end of month - No Leaves/ No Training | WIP
7 | Multiple project ID for entire month - starting from beginning/middle of month to middle/end of month - No Leaves/ No Training | WIP
8 | Multiple Project ID for entire month with Leave - no training code | WIP
9 | Multiple Project ID for entire month with training code - no leave | WIP
10 | Multiple Project ID for entire month with leaves and single/multiple training code | WIP
*Public Holiday scenario is already covered for all timecards for the month of January.